## Slide 1: WP4 as of July 2017 Oslo
Diego R. Lopez (TID)

## Slide 2: General Landscape
Doing reasonably well
  Deliverables on time
  The Observatory and FIRE fronts
Standardization fronts
  IETF/IRTF (QUIC, TSVWG, PANRG…) and ETSI NFV (MCP, measurement support, STAR)
  Doing IETF hackathons – One-bit and STAR
  What to do with ETSI CYBER
  Do we want to collaborate with IEEE ETIWG
Publications
  Fine, including a joint workshop with MONROE
  High-impact targets?
Exploitation
  The industrial workshop matter
  GSMA experiments
  The opportunity with security vendors (SYMANTEC)
  Contributing to FD.io/OSM/OPNFV/…
Public Communication
  Metering Observatory accesses and software downloads

## Slide 3: Reminder on WP4 Deliverables and Milestones
D4.1 - Data Management Plan. M4
D4.2 - Initial Standardisation, Dissemination, and Exploitation Report. M6
MS4 - External Middlebox Observatory Release. M12
  Released on March
MS6 - Knowledge exchange on FIRE. M18
  Is enough the recent workshop with MONROE?
D4.3 - Intermediate Standardisation, Dissemination, and Exploitation Report. M18
MS8 - Presentation of results to industry. M23
  Direct possibilities: The Hague (October), London (March), Paris (March), Madrid (May)
MS11 - Presentation of measurement techniques and results to academia. M29
D4.4 - Final Standardisation, Dissemination, and Exploitation Report. M30

## Slide 4: The ETSI CYBER and IEEE ETIWG Issues (I Know, Hic Sunt Leones…)
Trying to go beyond the transparent, MITM decrypting proxy
New work-item, CYBER0027
  “Middlebox Security Protocol – Part 1”
  Properties of such a protocol and possible implementations
  Considering mcTLS, mbTLS, an intended “mcIPsec”…
  Some potential points of collaboration
    MCP signalling
    STAR or even delegated certificates
    Reputation schemas based on endpoint declarations
The IEEE ETIWG
  Not chartered to build standards (yet)
  An industry reflection group
  Recently launched a manifest on the rationale for endpoint-aware traffic inspection
Do we want to collaborate with them (as a project)?
  Analyze what they are doing
  Report it to our reviewers